## Tasks
# | Deliverables | Urgency | Effort | Ext. | % | Days | Yield | Note | #
| Services agreement signed | 1 | 2 |  | 2.096% | 1.2579 |  | Billing/liab. Insurance by MBO Partners
| Key resources / partners | 2 | 4 | 4 | 4.193% | 2.5157 |  | Relationships
| Cities/regions targets list | 2 | 3 | 3 | 3.145% | 1.8868
5 | Conferences to participate (sign up deadlines) | 2 | 2 | 10 | 2.096% | 1.2579 |  | Critical path
| Media themes (tweet handles) | 2 | 3 | 3 | 3.145% | 1.8868
| Demo software docker install scripts | 3 | 7 | 7 | 7.338% | 4.4025 |  | Into AWS
| Agents embedded into Centos | 3 | 8 | 8 | 8.386% | 5.0314 |  | FTW
| Benchmark software under test | 3 | 3 | 3 | 3.145% | 1.8868
| Benchmark data | 3 | 3 | 3 | 3.145% | 1.8868
| Benchmark generation runs | 3 | 6 | 6 | 6.289% | 3.7736 |  | Show Sumo's value
| Benchmark publication | 3 | 3 | 3 | 3.145% | 1.8868 |  | blogs and articles
| Publishing timing | 4 | 2 | 2 | 2.096% | 1.2579
| Webinar capabilities (website, graphics, editors) | 4 | 2 | 2 | 2.096% | 1.2579
3 | Webinar recordings | 4 | 6 | 18 | 6.289% | 3.7736 |  | multi-use
3 | Blog articles text writing | 4 | 6 | 18 | 6.289% | 3.7736
30 | Tweet text and timings | 4 | 2 | 60 | 2.096% | 1.2579
| Spiffs to hand out | 4 | 1 | 1 | 1.048% | 0.62893
2 | Conference participation | 5 | 8 | 16 | 8.386% | 5.0314 |  | within initial timeframe
| Meetups setup in partner cities | 5 | 3 | 3 | 3.145% | 1.8868
10 | Meetups at cities | 5 | 10 | 100 | 10.48% | 6.2893
12 | Weekly status |  | 8.4 | 100.8 | 8.805% | 5.283
3 | Company events |  | 3 | 9 | 3.145% | 1.8868

## Totals
# | Deliverables | Urgency | Effort | Ext. | % | Days | Yield | Note | #
|  |  | 95.4 |  |  | 60